## PROJ MGMT TRACKING
CONTRIBUTORS
| Milestones | Tyler | Ron | Brandon | STATUS | COMPLETE %
M -1 | Draft project proposal | 0 | 1 | 0 | Complete | 100
M -2 | Setup git repo GIT LINK : https://github.com/BrandinO771/viper_proj_1.git | 0 | 0 | 1 | Complete | 100
M -3 | Draft project management template | 0 | 0 | 1 | Complete | 100
M -3 | Project Proposal Considerations: | - | - | - | - | -
M -4 | Select 5 medical procedures to evaluate | 1 | 1 | 1 | PENDING | 0
M -5 | Look at national vs one or two states | 0 | 0 | 0 | PENDING | 0
M -6 | use DRG code Charge Master | 0 | 0 | 0 | PENDING | 0
M -7 | Develop Correlation Hypothesis to explain or highlight findings | 0 | 0 | 0 | PENDING | 0
| TOTALS | 1 | 2 | 3
| Data: | Tyler | Ron | Brandon | Due Beginning Tuesday 9/3
D-1 | data considerations - for similar time periods , for same 5 medical procedure DRG codes, for similar markets California, NY, Mass | 0 | 0 | 0 | INCOMPLETE
D-2 | identify - & - access data sources: CSV | 1 | 1 | 1 | ONGOING
| identify - & - access data sources: API | 0 | 0 | 1 | ONGOING
D-3 | dump data set candidates (min of 1 file per contributor) PUSH TO GIT | 1 | 1 | 1 | ONGOING
D-4 | select data sets to utilize | 0 | 0 | 0 | INCOMPLETE
D-5 | create possible correlation Hypothesis for anomolies in charges detected | 0 | 0 | 0 | INCOMPLETE
| TOTALS | 2 | 2 | 3
| Pandas Work : | Tyler | Ron | Brandon | Due Begininig of Thursday 9/5
P-1 | data cleaning | 0 | 0 | 0 | PENDING
P-2 | data grouping | 0 | 0 | 0 | PENDING
| group or merge on : | - | - | - | -
| by hospital / DRG code | - | - | - | -
|  | - | - | - | -
P-3 | Overlay /incorporate following data : | 0 | 0 | 0 | PENDING
A | census data (racial, income, population demographics), | 0 | 0 | 0 | PENDING
B | patient satisfaction, | 0 | 0 | 0 | PENDING
C | procedure success rate | 0 | 0 | 0 | PENDING
E | physician compensation | 0 | 0 | 0 | PENDING
F | hospital profitability | 0 | 0 | 0 | PENDING
| TOTALS | 0 | 0 | 0
| MatplotLib Work: | Tyler | Ron | Brandon | Due Beginning of Sat 9/7
MP-1 | * Matplotlib to create a total of 6-8 visualizations of your data (ideally, at least 2 per "question" you ask of your data) |  |  |  | PENDING
MP-2 |  |  |  |  | PENDING
MP-3 |  |  |  |  | PENDING
MP-4 |  |  |  |  | PENDING
MP-4 |  |  |  |  | PENDING
PENDING
| TOTALS | 0 | 0 | 0
| Persentation Work / PRESENT ON TUESDAY SEPT 10TH | Tyler | Ron | Brandon | Due 75% complete Sat 9/7
P-1 | * [ ] Be at least 8-10 min. long |  |  |  | PENDING
P-2 | * [ ] Describe the core message or hypothesis for your project. |  |  |  | PENDING
P-3 | * [ ] Describe the questions you and your group found interesting, and what motivated you to answer them |  |  |  | PENDING
P-4 | * [ ] Summarize where and how you found the data you used to answer these questions |  |  |  | PENDING
P-5 | * [ ] Describe the data exploration and cleanup process (accompanied by your Jupyter Notebook) |  |  |  | PENDING
P-6 | * [ ] Describe the analysis process (accompanied by your Jupyter Notebook) |  |  |  | PENDING
P-7 | * [ ] Summarize your conclusions. This should include a numerical summary (i.e., what data did your analysis yield), as well as visualizations of that summary (plots of the final analysis data) |  |  |  | PENDING
P-8 | * [ ] Discuss the implications of your findings. This is where you get to have an open-ended discussion about what your findings "mean". |  |  |  | PENDING
P-9 | * [ ] Tell a good story! Storytelling through data analysis is no different than in literature. Find your narrative and use your analysis and visualization skills to highlight conflict and resolution in your data. |  |  |  | PENDING
Note on I15: brandon steinke: DATA CLEANING NOTES FROM RON: *ucdavis_drg_clean - only has DRG total description *ucsd AND ucsf_drg_clean -- WIll need to string separate DRG code from total description *Mass. hospitals have MS### as the drg code. Needs stripping in Python
Note on I27: brandon steinke:

## Proj Detail
Milestones Detail
| MEDICAL PROCEDURE NAME : ( LIST 5-7 ) | DRG CODE
1 | 871 (Septicemia) | 871
2 | 470 (major joint replace) [ specify knee or hip ] | 470
3 | 291 (Heart Failure) | 291
4 | 392 GI / Digestive disorders | 392
5 | ???
STATE NAMES:
1
2
3
CITY NAMES :
1
2
3
4
5
6
7
KEY FINDINGS :
1
2
3
4
5
6
7
LIST TEST HYPOTHESIS FOR CORRELATIONS :
1
2
3
4
5
ADDITIONAL DATA TO COMPARE TO MEDICAL DATA
1
2
3
4
5
6
RESULTS OF HYPOTHESIS TESTING :
1
2
3
4
5
ADDITIONAL HYPOTHESIS OR REALIZATIONS FROM RESEARCH
1
2
3
4
5
6
7

## data reference links
ALL DATA RESOURCE INFORMATION
| Dumper | Cleaner | Merger | DATA CHARTED | API puller | locator | PROJ MGMT UPDATOR | BRIEF DATA DESCRIPTION | FILE NAME : | DATA TIME PERIOD (YEAR): | DATA TYPE (API, CSV, API DOC, WEB INFO, VISUAL, DATA REPOS): | API USER NAME | API KEY | API DICTIONARY NAMES | DATA LOCATION INFO PAGE URL : | DATA DOWNLOAD LINK
1 | B | 0 | 0 | 0 | B | B | B | MEDICARE API : | ? | ? | API | ? | 3gmjva0k2nclbmridbdz8x6qi |  | https://data.medicare.gov/developers | https://dev.socrata.com/foundry/data.medicare.gov/vv6z-qryr
2 | B | 0 | 0 | 0 | 0 | R | B | MEDICARE CHARGE INFO NATIONAL | Inpatient_Prospective_Payment_System__IPPS__Provider_Summary_for_the_Top_100_Diagnosis-Related_Groups__DRG__-_FY2011 | 2011-2014 ? | CSV | N/A | N/A | N/A | https://data.cms.gov/Medicare-Inpatient/Inpatient-Prospective-Payment-System-IPPS-Provider/97k6-zzx3 | https://data.cms.gov/api/views/97k6-zzx3/rows.csv?accessType=DOWNLOAD&bom=true&format=true
3 | B | 0 | 0 | 0 | 0 | 0 | B | API DOCS FOR MEDICARE CHARGE INFO NATIONAL FILE | ? | ? | API DOC | ? | 3gmjva0k2nclbmridbdz8x6qi | ? | https://dev.socrata.com/foundry/data.cms.gov/ehrv-m9r6
4 | R | 0 | 0 | 0 | 0 | R | B | CALIFORNIA CHART MASTER DATA | ? | ? | INFO | N/A | N/A | N/A | https://oshpd.ca.gov/data-and-reports/topics/
5 | B | 0 | 0 | 0 | 0 | B | B | MAPPING MEDICARE DISPARITIES | customize national web based data visualization by year and downloads | ? | ? | N/A | N/A | N/A | https://data.cms.gov/mapping-medicare-disparities
6 | B | 0 | 0 | 0 | 0 | B | B | COST FOR PATIENTS PROCEDURES, FOR HEARTH ATTACKS -- 13K ROWS OF ALL TYPES OF PROCEDURE PAYMENTS AND IF ABOVE OR BELOW THE NATIONAL AVG ¦ CSV | Payment_and_value_of_care_-_Hospital | ? | CSV | N/A | N/A | N/A | see download link --> | https://data.medicare.gov/api/views/c7us-v4mf/rows.csv?accessType=DOWNLOAD
7 | B | 0 | 0 | 0 | 0 | B | B | LATEST HCUP-BASED STATISTICS FOR HEALTH CARE INFORMATION | ? | ? | VISUAL | N/A | N/A | N/A | https://www.hcup-us.ahrq.gov/faststats/landing.jsp
8 | B | 0 | 0 | 0 | 0 | B | B | (AHRQ GOV) AGENCY FOR HEALTHCARE RESEARCH AND QUALITY | The Agency for Healthcare Research and Quality (AHRQ) offers practical, research-based tools and other resources to help a variety of health care organizations, providers and others make care safer in all health care settings. | ? | DATA REPO | N/A | N/A | N/A | https://www.ahrq.gov/data/resources/index.html
9 | B | 0 | 0 | 0 | 0 | B | B | OSHPD CHARGEMASTERS | CAL - Office State Health Planning Development | 2011-2018 | DATA REPO | N/A | N/A | N/A | https://oshpd.ca.gov/data-and-reports/cost-transparency/hospital-chargemasters/2018-chargemasters/
10 | B | 0 | 0 | 0 | 0 | R | B | CMS.GOV (CENTERS FOR MEDICARE/MEDICADE SERVICES | OutPatient Charge Data CY 2017 | ? | DATA REPO | N/A | N/A | N/A | https://www.cms.gov/Research-Statistics-Data-and-Systems/Statistics-Trends-and-Reports/Medicare-Provider-Charge-Data/Outpatient2017.html
11 | B | 0 | 0 | 0 | 0 | B | B | NATIONAL PATIENT SURVEY 2017-2018 ABOUT THEIR STAY AT HOSPITAL | Patient_survey__HCAHPS__-_State | 2017-2018 | CSV | N/A | N/A | N/A |  | https://data.medicare.gov/api/views/84jm-wiui/rows.csv?accessType=DOWNLOAD
12 | B | 0 | 0 | 0 | 0 | B | B | 20 years of hospital trends, stay length, cost, demographics | HCUP_National_TrendsInpatientStays_DataExport | 1994-2015 | CSV | N/A | N/A | N/A |  | https://files.slack.com/files-pri/TJYDCA20Z-FMTL36YE9/download/hcup_national_trendsinpatientstays_dataexport.xls
14 | R | 0 | 0 | 0 | 0 | R | B | SEE DESCRIPTS BELOW | data dump/CA UC Health Data.zip | 2018/2019 | ? | ? | ? | ? | ? | ?
15 | R | 0 | 0 | 0 | 0 | R | B | SEE DESCRIPTS BELOW | ata dump/MA Partners Healthcare Data.zip | 2018/2019 | ? | ? | ? | ? | ? | ?
16 | R | 0 | 0 | 0 | 0 | R | B | SEE DESCRIPTS BELOW | data dump/MI McLaren Healthcare Data.zip | 2018/2019 | ? | ? | ? | ? | ? | ?
17 | R | 0 | 0 | 0 | 0 | R | B | SEE DESCRIPTS BELOW | data dump/nyp_hudson_valley_drg.xlsx | 2018/2019 | XLSX | ? | ? | ? | ? | ?
18 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES /DRG CODES / SINGLE MED FACILITY | CDH_drg_clean.xlsx | 2018/2019 | XLSX | ? | ? | ? | ? | ?
19 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES /DRG CODES / SINGLE MED FACILITY | MGH_drg_clean.xlsx | 2018/2019 | XLSX | ? | ? | ? | ? | ?
20 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES /DRG CODES / SINGLE MED FACILITY | MVH_drg_clean.xlsx | 2018/2019 | XLSX | ? | ? | ? | ? | ?
21 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES /DRG CODES / SINGLE MED FACILITY | NCH_drg_clean.xlsx | 2018/2019 | XLSX | ? | ? | ? | ? | ?
22 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES /DRG CODES / SINGLE MED FACILITY | NSMC_drg_clean.xlsx | 2018/2019 | XLSX | ? | ? | ? | ? | ?
23 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES /DRG CODES /NEWTON-WELLESLEY HOSPITAL/HOSP CHGS/PHARMCY CHGS | NWH_drg_clean.xlsx | 2018/2019 | XLSX | ? | ? | ? | ? | ?
24 | R | R | 0 | R | 0 | R | B | PYMT AMTS, NO DRG, NAT PROVDRS, PYMT AMT CATEGRZD, PROCEDURE RESULT CATEGRZD | Payment_and_value_of_care_-_Hospital_CLEAN.xlsx | 2018/2019 | XLSX | ? | ? | ? | ? | ?
25 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES /DRG CODES / 11 MED FACILITIES | mclaren_health_drg_clean.csv | 2018/2019 | CSV | ? | ? | ? | ? | ?
26 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES /DRG CODES / SINGLE MED FACILITY | nyp_hudson_valley_drg_clean.xlsx | 2018/2019 | XLSX | ? | ? | ? | ? | ?
27 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES / !!NO DRG CODES /DRG DESCRIP | ucdavis_drg_clean.csv | 2018/2019 | CSV | ? | ? | ? | ? | ?
28 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES /DRG CODES / SINGLE MED FACILITY | ucsd_drg_clean.csv | 2018/2019 | CSV | ? | ? | ? | https://health.ucdavis.edu/newsroom/public-reporting/chargemaster.html | ?
29 | R | R | 0 | 0 | 0 | R | B | MEDIAN DRG CHARGES /DRG CODES / SINGLE MED FACILITY | ucsf_drg_clean.csv | 2018/2019 | CSV | ? | ? | ? | https://health.ucdavis.edu/newsroom/public-reporting/chargemaster.html | ?
30 | R | R | 0 | 0 | 0 | R | B | How a DRG Determines How Much a Hospital Gets Paid | How a DRG Determines How Much a Hospital Gets Paid | ? | WEB BLOG/ARTICLE | N/A | N/A | N/A | https://www.verywellhealth.com/how-does-a-drg-determine-how-much-a-hospital-gets-paid-1738874
31 | R | R | 0 | 0 | 0 | R | B | Top 10 Inpatient Diagnoses by DRG Codes | Top 10 Inpatient Diagnoses by DRG Codes | ? | WEB BLOG/ARTICLE | N/A | N/A | N/A | https://blog.definitivehc.com/top-10-inpatient-diagnoses-by-drg-codes
32 | R | R | 0 | 0 | 0 | R | B | Top 10 Inpatient Diagnoses by DRG Codes | Top 10 Inpatient Diagnoses by DRG Codes | ? | WEB BLOG/ARTICLE | N/A | N/A | N/A | https://www.hiacode.com/education/most-common-drgs-with-recommendations-2018-part-1/
32 | 0 | 0 | 0 | 0 | T | T | B | hospital scores/ratings/ Zip codes National/ Faclty Name | Hospital_Compare_Scores___Ratings |  | CSV |  |  |  | https://www.cms.gov/icd10manual/fullcode_cms/p0031.html
32 | 0 | 0 | 0 | 0 | 0 | B | B | LIST OF ALL DRG CODES
32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project Guidelines
# Presentation Guidelines
You are free to structure your presentations to your liking, but students tend to have success with the following format.
* Title Slide
* Include the name of the Project and Group Members
* Motivation & Summary Slide
* Define the core message or hypothesis of your project.
* Describe the questions you asked, and _why_ you asked them
* Describe whether you were able to answer these questions to your satisfaction, and briefly summarize your findings
* Questions & Data
* Elaborate on the questions you asked, describing what kinds of data you needed to answer them, and where you found it
* Data Cleanup & Exploration
* Describe the exploration and cleanup process
* Discuss insights you had while exploring the data that you didn't anticipate
* Discuss any problems that arose after exploring the data, and how you resolved them
* Present and discuss interesting figures developed during exploration, ideally with the help of Jupyter Notebook
* Data Analysis
* Discuss the steps you took to analyze the data and answer each question you asked in your proposal
* Present and discuss interesting figures developed during analysis, ideally with the help of Jupyter Notebook
* Discussion
* Discuss your findings. Did you find what you expected to find? If not, why not? What inferences or general conclusions can
The technical requirements for Project 1 are as follows.
* [ ] Use Pandas to clean and format your data set(s)
* [ ] Create a Jupyter Notebook describing the **data exploration and cleanup** process
* [ ] Create a Jupyter Notebook illustrating the **final data analysis**
* [ ] Use Matplotlib to create a total of 6-8 visualizations of your data (ideally, at least 2 per "question" you ask of your data)
* [ ] Save PNG images of your visualizations to distribute to the class and instructional team, and for inclusion in your presentation
* [ ] Optionally, use at least one API, if you can find an API with data pertinent to your primary research questions
* [ ] Create a write-up summarizing your major findings. This should include a heading for each "question" you asked of your data, and under each heading, a short description of what you found and any relevant plots.
The presentation requirements for Project 1 are as follows.
Your presentation must:
* [ ] Be at least 8-10 min. long
* [ ] Describe the core message or hypothesis for your project.
* [ ] Describe the questions you and your group found interesting, and what motivated you to answer them
* [ ] Summarize where and how you found the data you used to answer these questions
* [ ] Describe the data exploration and cleanup process (accompanied by your Jupyter Notebook)
* [ ] Describe the analysis process (accompanied by your Jupyter Notebook)
* [ ] Summarize your conclusions. This should include a numerical summary (i.e., what data did your analysis yield), as well as visualizations of that summary (plots of the final analysis data)
* [ ] Discuss the implications of your findings. This is where you get to have an open-ended discussion about what your findings "mean".
* [ ] Tell a good story! Storytelling through data analysis is no different than in literature. Find your narrative and use your analysis and visualization skills to highlight conflict and resolution in your data.
# Technical Requirements

## contributions
PROJECT CONTRIBUTIONS
Milestones | name | name | name
Conceptualize project | Tyler | Ron | Brandon
Probe web for data | Tyler | Ron | Brandon
Draft project proposal | 0 | Ron | 0
Setup git repo GIT LINK : | 0 | 0 | Brandon | https://github.com/BrandinO771/viper_proj_1.git
create project mgmt template | 0 | 0 | Brandon
provide data files | Tyler | Ron | Brandon
cleaned / formatted data files
merge / grouped data files
``

## TERMS
WITHIN THE DRG CODE DEFINITION YOU WILL SEE 'WITH CC OR MCC '
ABBR | SHORT DEF | LONG DEF
CC | complication or comorbidity | the simultaneous presence of two chronic diseases or conditions in a patient.
MCC | major complication or comorbidity | (MCC) when used as a secondary diagnosis
PART 2 | Part 2 lists codes which are assigned as a Major CC only for patients discharged alive.
Appendix C is a list of all of the codes that are defined as either a complication or comorbidity (CC) or a major complication or comorbidity (MCC) when used as a secondary diagnosis. …
SELECTED DRG CODES
DRG CODE | SHORT DEF | LONG DEF
871 | Septicemia | 871 - SEPTICEMIA OR SEVERE SEPSIS W/O MV 96+ HOURS W MCC
470 | major joint replace | 470 - MAJOR JOINT REPLACEMENT OR REATTACHMENT OF LOWER EXTREMITY W/O MCC
291 | Heart Failure | 291 - HEART FAILURE & SHOCK W MCC
392 | GI / Digestive disorders | 392 - ESOPHAGITIS, GASTROENT & MISC DIGEST DISORDERS W/O MCC
638 | 638 - DIABETES W CC
LONGER DEFINITIONS AND OTHER CODES
DRG CODE | SHORT DEF | LONG DEF
392 | 392 - ESOPHAGITIS, GASTROENT & MISC DIGEST DISORDERS W/O MCC | Gastroenterology Disease It includes common and important conditions such as colon polyps and cancer, hepatitis, gastroesophageal reflux (heartburn), peptic ulcer disease, colitis, gallbladder and biliary tract disease, n
392 | 392 - ESOPHAGITIS, GASTROENT & MISC DIGEST DISORDERS W/O MCC | Eosinophilic Esophagitis (EoE) Eosinophilic (ee-uh-sin-uh-fil-ik) esophagitis (EoE) is a recognized chronic allergic/immune condition. A person with EoE will have inflammation of the esophagus. ...
280 | 280 - ACUTE MYOCARDIAL INFARCTION, DISCHARGED ALIVE W MCC | Acute myocardial infarction is the medical name for a heart attack. A heart attack isa life-threatening condition that occurs when blood flow to the heart muscle isabruptly cut off, causing tissue damage. This is usually the result of a blockage in one or more of the coronary arteries.
303 | 303 - ATHEROSCLEROSIS W/O MCC | Atherosclerosis is a disease in which plaque builds up inside your arteries. Arteries are blood vessels that carry oxygen-rich blood to your heart and other parts of your body. Plaque is made up of fat, cholesterol, calcium, and other substances
418 | 418 - LAPAROSCOPIC CHOLECYSTECTOMY W/O C.D.E. W CC | A laparoscopic cholecystectomy is a surgery during which the doctor removes yourgallbladder.
638 | 638 - DIABETES W CC | Diabetes is a disease that occurs when your blood glucose, also called blood sugar, is too high. ... Insulin, a hormone made by the pancreas, helps glucose from food get into your cells to be used for energy.
664 | 664 - MINOR BLADDER PROCEDURES W/O CC/MCC